## Slide 1: Handover Process overview from ITD to Ops Release Management for ITD base projects
13th May 2013

## Slide 2
Objective
Release Management process overview
Understand the transition process from Development to Ops team.
Scope of Project and Ops team as part of transition.
Transition check list
Summary
Next steps

## Slide 3: Definition and Process in brief
Release Management is a process to improve reliability of Web & Mobile sites by professionalizing the process of pushing new code and solutions to production.
  It helps to plan, manage and control the release schedule and track the status of each release effectively
  It enables to deliver service on expected level starting from 1st day after launch
  Types of releases:
    ITD projects
    M&O changes – Already Deployed
    Emergency fixes – Already Deployed
Notes: ITD projects – containing large area of new functionality / website which are introduced under ITD umbrella (major changes & launches of new sites)
M&O changes – led by ITO, containing enhancements and fixes to existed websites
Emergency fixes – containing the corrections to a small number of Known errors

## Slide 4: Definition and Process in brief (Cont)
Standard M&O Changes | Emergency Changes | Project Releases
Migrated during specific window defined For P3 incidents, migration window holds good unless it has impact on SLA. | No defined migration window for P1 & P2 incidents | - Project releases needs to happen as per the CPS, the checklist should be similar to M&O changes. However, Savvis should be intimated well in advance to turn the Gomez monitoring off.
Exception to migrate outside release window (for CRs and P3 incidents) to be approved by Ops Lead. Request for exception should come from Operation specialist or DPDL Main criterium for NO GO is visible risk on service stability. | Can be migrated any time once the fix is ready after basic testing is completed by Technical Agency | - The Dev and Ops specialists should be in sync, along with the project resources during the go live. The transition checklist needs to be verified and updated as per the latest status.
Release checklist should be attached before closure of the ticket in HPSM RM measures should be updated in the solution field of HPSM ticket before closure of the ticket. |  | The checklist provided in the DevtoOps deck needs to be updated and should be submitted to ops lead for sign off.
Release Checklist to be updated by Operation Specialist and Technical Agency (based on owner of the tasks in it) | Simplified version of the Release checklist to be updated by Operation Specialist and Technical Agency (based on owner of the tasks in it) | The release and project checklist should be updated by project team
NEW
ALREADY DEPLOYED

## Slide 5: M&O changes
Build and Unit Test
By Technical Agency
UAT
In Staging
By Requestor or Ops specialist
Resolve
By Technical Agency
After validating production push
Close
By Ops specialist
After validation by Requestor or Ops specialist
Open
By Ops Specialist
Build and Unit Test
By Technical Agency
Testing (UAT)
By Dev specialist and creative/Brand
Go-live/Hypercare
By Technical Agency (Dev and Ops Team)
Validation co-ordination by Dev and Ops Specialists
Go live Support
By Ops specialist with ticket requests
Tech agency M&O team responding to the requests
Kickoff/Design
By Dev Specialist and Tech agency
In Staging
Project Releases

## Slide 6: Release Management process for ITD base projects

## Slide 7
Handover Process overview from ITD to Ops
Kick-off
Design
Build
SIT
UAT
Launch/Go-live
Hypercare
Production Support
ITD/Project Team
Operations
Phase Owner
Transition to Ops Process
 |  |  |  |  | For new Incidents |  | 
Transition plan owner (Ops checklist)
Knowledge transfer (as described in checklist)
Securing access to Ops teams
Fixing all project related issues detected before launch
Transition to Ops completed (obtain Ops Leads sign-off)
Hypercare completed (obtain Ops Leads sign-off)
Legend:
Dev Team
Project Team
Operations

## Slide 8
Handover Process overview from ITD to Ops
Kick-off
Design
Build
SIT
UAT
Launch/Go-live
Hypercare
Production Support
ITD/Project Team
Operations
Phase Owner
Incidents/Changes
As agreed in Project Scope | Ops Ticketing System | 
As agreed in Project Scope | Regular Ops SLAs | 
As agreed in Project Scope |  | 
 | Ops (With Project team support) | 
 | Ops (With Project team support) | 
Defects / Incidents / Change requests tracking
SLAs for resolution
Ownership of communication for incidents
Regular Hypercare reports
Ownership of new defects (depends on detection phase)
Ownership of M&O changes
Legend:
Dev Team
Project Team
Operations

## Slide 9
Handover Process overview from ITD to Ops
Kick-off
Design
Build
SIT
UAT
Launch/Go-live
Hypercare
Production Support
ITD/Project Team
Operations
Phase Owner
Support
 |  | Ops Regular support in place | 
 |  | Ops Specialists | 
 |  | Tech agency Ops Team | 
Support hours
1st / 2nd level of support
3rd level of support
Extended 3rd level of support
Legend:
Dev Team
Project Team
Operations

## Slide 10
Handover Process overview from ITD to Ops
Kick-off
Design
Build
SIT
UAT
Launch/Go-live
Hypercare
Production Support
ITD/Project Team
Operations
Phase Owner
Reporting
 | Only if QD is reported | 
QoD (incl. quality of product)
Ops QD score calculation
Reporting of QD scores for new launches
Reporting of QD scores for project for existing sites
Apps Health scores
#SI calculation
Legend:
Dev Team
Project Team
Operations

## Slide 11
Handover process checklist from ITD to Ops

## Slide 12: Key summary notes
Ops team is responsible for quality of service for new project starting from 1st day after launch
Project (Dev Specialist) is accountable for quality preparing of new service for Operations. But collaboratively to be worked with Project team.
Ops Specialist must be engaged no later than before SIT ends OR 10WD before launch – whatever comes first
New site should be fully configured in all Ops tools (as mentioned in the checklist) and in EZ no later than 2 WD after launch

## Slide 13: Next steps
Start using the process effective 1st July.
Feedback from Ops and Dev Team on a weekly basis to the Ops Leads as what is working and what is not by emails.
Review calls Bi-weekly with Ops Managers.