## Process Overview
Handover Process Overview for ITD base project (base work)
Project phases
| Kick-off | Design | Build | SIT | UAT | Launch | Hypercare | Production
phase owner | ITD / project team | [6 empty] | Operations
Transition to Ops process
transition plan owner (Ops checklist) |  |  |  | project team
knowladge transfer (as it is described in checklist) | [6 empty] | for new incidents
securing access for Ops teams
fixing all project related issues detected before launch | project team | [6 empty] | Operations
transition to Ops completed (obtain Ops Lead sign-off)
hypercare completed (obtain Ops Lead sign-off)
incidents / changes
defects / incidents / change requests tracking | as agreed in project scope | [5 empty] | Ops ticketing system
SLAs for resolution | as agreed in project scope | [5 empty] | regular Ops SLAs
ownership of communication for incidents | as agreed in project scope | [5 empty] | project team | Ops
regular hypercare reports | [6 empty] | project team
ownership of new defects (depends on detection phase) | project team | [5 empty] | Ops (with project team support) | Ops
ownership of M&O changes | [6 empty] | Ops (must coordinate with project team) | Ops
support
support hours | as agreed in project scope | [5 empty] | regular support in place
1st / 2nd level of support | n/a |  |  |  | project team |  | Ops (Ops Spec)
3rd level of support | project team | [5 empty] | Ops (Technical Agency Ops team)
extended 3rd level of support | n/a | [5 empty] | project team | n/a
reporting
QoD (incl. quality of product) | project team | [6 empty] | n/a
Ops QD score calculation | [6 empty] | Ops
Reporting of QD scores for new launches | n/a | [6 empty] | Ops
Reporting of QD scores for project for existing sites | n/a | [5 empty] | Ops
Apps Health scores | project team | [5 empty] | Ops
#SI calculation | n/a | [5 empty] | Ops (only if QD is reported) | Ops

## DevToOps Checklist
# | Question | Task Owner | Status | Remarks
DevToOps Checklist is owned by Project Team
No later than SIT end / 10WD before launch – whatever comes first
1.1 | Ops Specialist is assigned to the site | Ops Lead | in-progress
1.2 | Master URL is defined (main, unique url which will be used for configuration of all Ops tools) | Ops Lead | in-progress
1.3 | List of existing defects identified during SIT tests and ETA to solve them is shared | Project Team | in-progress
1.4 | TP ID (Touchpoint id) for new site is created in EZ | Project Team | in-progress
1.5 | Request for providing access for all environments for Ops teams is sent to hosting team | Project Team | in-progress
No later than UAT end / 5 WD before launch – whatever comes first
2.1 | UAT tests results are collected and reported | Project Team | in-progress
2.2 | UAT tests results are reviewed | Ops Specialist | in-progress
2.3 | Configuration Item for new website is added to HP SM SaaS | Ops Specialist | in-progress
2.4 | Optional recommended inital check of Apps Health Scores are met for Staging (expected target on PROD is PageSpeed >70, Yslow>70, %of CDN implementation >70%). In case of issue, will be addressed by project team in hypercare period. | Project Team | in-progress
2.5 | Information about website (for master url) is properly displayed in Savvis CMDB (valid from May13) | Ops Specialist | in-progress
2.6 | Ops team in TA confirms full access to all environments | TA Ops Team | in-progress
2.7 | PSAT scans on Staging are passed | Project Team | in-progress
2.8 | Website documentation is uploaded to docs repository on Technical Agency Ops side | Project Team | in-progress
2.9a | a) Logical Architecture of the application | Project Team | in-progress
2.9b | b) Tools Used, i.e list the programming language, development tools and any third-party products used | Project Team | in-progress
2.9c | c) Database/Data Model | Project Team | in-progress
2.9d | d) Other avaliable documentation | Project Team | in-progress
2.10 | Hyperlink to Staging has been delivered to Ops Specialist | Project Team | in-progress
2.11 | Traffic forecast has been delivered by business | Project Team | in-progress
2.12 | All mandatory fields are filled in EZ with quality (details in next worksheet) | Project Team | in-progress
Not later than 2 WD before launch
3.1 | Latest source code been setup in the development & Staging environment (they should be in sync) | Project Team | in-progress
3.2 | Training to M&O (Maintenance and Operation) team of Agency from Development team of Agency is completed | Project Team | in-progress
3.3 | Training From Dev Spl to Ops Spl is completed | Ops Specialist | in-progress
3.4 | Ops team on TA side confirmed full readiness for providing M&O support | TA Ops Team | in-progress
3.5 | [for exisiting websites] Backout plan for migration has been created | Project Team | in-progress
3.6 | [for existing websites] Communcation about downtime (needed for project migration to PROD) has been sent | Project Team | in-progress
3.7 | Completness of transition is confirmed by Ops (Ops Lead sign-off) | Project Team | in-progress
Launch (+/- 2 WD)
4.1 | PSAT scans are passed on Production | Project Team | in-progress
4.2 | Website is added to Gomez / Pingdom (results should be a part of hypercare report sent by project team) | Ops Specialist | in-progress
4.3 | Website is added to ShowSlow (incl. CDN utilization) | Ops Specialist | in-progress
4.4 | Verify if the website is added to GAP else raise a request with WebAnalytics team | Ops Specialist | in-progress
4.5 | Deliver list of all not closed UAT incidents, approval for GO life with them and commited resolution date | Project Team | in-progress
4.6 | Problem Records are created in HP SM SaaS for all open defects not solved before launch | Ops Specialist | in-progress
4.7 | Resolution time for all open defects is provided (not later than before hyparcare end), ETA included in PM tickets | Ops Specialist | in-progress
4.8 | Targets for Apps Health Scores are met for Production (PageSpeed >70, Yslow>70, %of CDN implementation >70%) | Ops Specialist | in-progress
4.9 | WebOps Capability Name is Active status in EZ, mandatory fields are properly filled in EZ | Project Team | in-progress
4.10 | If website is connected to 1CP, add new site to official list of 1CP interfaces (box.net) | Ops Specialist | in-progress
Before hypercare end
5.1 | All open PRs (defects during previous project phases are fixed) | Project Team | in-progress
5.2 | Targets for Apps Health Scores are met - final check | Project Team | in-progress
5.3 | Hypercare is completed - Ops sign-off (by Ops Lead) | Project Team | in-progress

## Resources&Transition
Project Details
Project Name
Brand
BU
Region
Start Date
End Date
Tech Agency Project Key contacts
Tech Agency Project Manager
Dev. Specialist
Ops Specialist
Milestones/Check Points | Owner | Start Date | End Date | Dev Specialist | Ops Specialist | Remarks
Transition to Ops Process
Incidents/Changes
Support
Reporting

## Mandatory information in EZ
The following information MUST be included / updated in EZ before project launch
| TP ID | TBC
| WebOps Capability Name | TBC
| Capability Status | Planning
| Field name | Status
| Category | to check
| Brand | to check
| Geographical Groups | to check
| Country | to check
| Language | to check
| Hosting URL | to check
| Instance Name | to check
| DMM: Contact Name | to check
| President DMM: Contact Name | to check
| DPDL: Contact Name | to check
| Web Ops Specialist: Contact Name | to check
| Web Dev Specialist: Contact Name | to check
| Tech Agency Ops: Contact Name | to check
| PII Data | to check

## Doc version
Dcoument type | DevToOps Checklist for ITD base projects
Version | 1.5 (May, 29, 2013)
Created by | Krzysztof Klodnicki (klodnicki.k@pg.com)